## CPRG Compliance Requirements
Source | Requirement and Citation | Category | Description | Frequency | Owner | Applicability | DEQ Action
Award Agreement | Programmatic Conditions - Section B: Final Approved Work Plan and Modifications | Reporting | Request written approval from the EPA on changes to budget or project scope or objective, and report these deviations to EPA within reporting requirements. | As Needed |  | Applicable | Request EPA approval to change the scope or objective of the project or program; change key personnel identified in the Federal award; for the disengagement from a project for more than three months, or a 25% reduction in time and effort devoted to the Federal award over the course of the period of performance, by the approved project director or principal investigator; for the inclusion of costs that require prior approval in accordance with 2 CFR Part 200 Subpart E—Cost Principles or 48 CFR part 31; for the transfer of funds budgeted for participant support costs as defined in 2 CFR Section 200.1 Definitions to other budget categories; for the subawarding, transferring or contracting out of any work under the award. Request approval and report to the Project Officer and Grant Specialist.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.204 Notices of funding opportunities. | Procurement & Contracting | Ensure the federal funding opportunity was publicly announced with all required elements before applying. | As Needed |  | Applicable | Download and file the official funding opportunity notice from Grants.gov or the federal agency’s site to confirm compliance and maintain audit records.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.318 General procurement standards. Conflicts of interest. | Procurement & Contracting | Maintain written standards of conduct to prevent conflicts of interest in procurement transactions under federal awards. | As Needed |  | Applicable | Verify that agency’s procurement policy includes conflict-of-interest provisions and ensure staff involved in purchasing acknowledge these standards before initiating any federally funded procurement.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.217 Whistleblower protections. | Procurement & Contracting | Recipients of federal funds must not retaliate against employees who disclose evidence of fraud, waste, or abuse related to the grant. | Ongoing |  | Applicable | Include whistleblower protection language in internal grant compliance policies and ensure employees are informed of their rights under 41 U.S.C. § 4712.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.303 Internal controls. | Procurement & Contracting | Maintain effective internal controls to ensure compliance with federal statutes, regulations, and the terms of the award. | Ongoing |  | Applicable | Document and implement written internal control procedures aligned with the Committee of Sponsoring Organizations of the Treadway Commission (COSO) framework to prevent fraud, waste, and noncompliance. Link to COSO framework: https://www.coso.org/guidance-on-ic.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.318 General procurement standards. | Procurement & Contracting | Follow documented procurement procedures that comply with state laws and federal requirements for goods and services under federal awards. | As Needed |  | Applicable | Review and apply agency’s written procurement policy to ensure it meets federal standards, including full and open competition, before initiating any purchase.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.512 Report submission. | Procurement & Contracting | Submit the Single Audit reporting package and Data Collection Form to the Federal Audit Clearinghouse (FAC) within the required timeframe. Annually, for each fiscal year in which agency expends $1,000,000 or more in federal funds. | Annually |  | Conditional | Prepare and upload the audit reporting package and completed Data Collection Form to the Federal Audit Clearinghouse within 30 days of receiving the auditor’s report or nine months after fiscal year-end, whichever is earlier.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.344 Closeout. | Procurement & Contracting | Complete all financial, performance, and administrative actions required to close out a federal award within the specified timeframe. | End of Project |  | Applicable | Submit all final financial, performance, and other required reports to the federal awarding agency within 120 days of the award’s end date.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.314 Supplies. | Procurement & Contracting | Manage and account for supplies purchased with federal funds, including disposition of unused supplies at closeout. | Ongoing |  | Conditional | Track all federally funded supplies in inventory and, at closeout, determine if unused supplies exceed $5,000 in aggregate; if so, calculate and remit the federal share or request disposition instructions.
Award Agreement ; EPA General Terms & Conditions | 2 CFR § 200.340 Termination. | Procurement & Contracting | Federal awards may be terminated by the agency, agency, or by mutual agreement for noncompliance, cause, or convenience. | As Needed |  | Applicable | Review termination provisions in the award agreement and, if initiating termination, provide written notice to the federal awarding agency with justification and proposed effective date.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.403 Factors affecting allowability of costs. | Procurement & Contracting | Costs charged to a federal award must be necessary, reasonable, allocable, and conform to applicable regulations and award terms. | Ongoing |  | Applicable | Verify each cost against the allowability criteria (necessary, reasonable, allocable, and consistent with agency policies) before approving payment or charging to the federal award.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.414 Indirect costs. | Procurement & Contracting | Recipients may recover indirect costs using a federally negotiated rate, an approved state-wide cost allocation plan, or the de minimis rate if eligible. | At award negotiation and whenever indirect costs are charged. |  | Applicable | Confirm agency’s approved indirect cost rate agreement or elect the 10% de minimis rate, then apply the correct rate to the federal award budget.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.308 Revision of budget and program plans. | Procurement & Contracting | Recipients must obtain prior written approval from the federal awarding agency for certain changes to budgets or program scope. | As Needed |  | Applicable | Identify any proposed changes that require prior approval (e.g., scope changes, key personnel changes, budget transfers exceeding thresholds) and submit a formal request to the federal awarding agency before implementing the revision.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.313 Equipment. | Procurement & Contracting | Establish and maintain control over equipment purchased with federal funds, including use, maintenance, and disposition. | Ongoing |  | Applicable | Create and maintain an equipment inventory record that includes description, serial number, location, and federal share, and ensure equipment is used for the authorized program purpose.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.425 Audit services. | Procurement & Contracting | Costs for audits required by Subpart F are allowable, but other audit costs are generally unallowable unless specifically approved. | One-time |  | Applicable | Confirm that audit costs charged to federal awards are limited to the Single Audit required under Subpart F and exclude any non-federal audit services unless prior written approval is obtained.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.514 Standards and scope of audit. | Procurement & Contracting | Ensure the Single Audit is conducted in accordance with Generally Accepted Government Auditing Standards (GAGAS) and covers compliance with federal program requirements. Annually, when agency expends $1,000,000 or more in federal funds. | One-time |  | Conditional | Engage an independent auditor to perform the Single Audit following Generally Accepted Government Auditing Standards and verify that the audit includes testing of internal controls and compliance for each major federal program. Submit a single audit report within 9 months of the end of DEQ's fiscal year or 30 days after receiving the report from an independent auditor. The single audit report MUST be submitted using the Federal Audit Clearinghouse available at: https://fac.gov/.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.415 Required certifications. | Procurement & Contracting | Certifications must accompany annual and final financial reports and requests for payment, attesting to the accuracy and completeness of submitted information. | One-time |  | Applicable | Ensure the authorized official signs the required certification statement affirming that the report or payment request is true, complete, and accurate before submission. Financial reports must include a certification, signed by an official who is authorized to legally bind the recipient, which reads as follows: “By signing this report, I certify to the best of my knowledge and belief that the report is true, complete, and accurate, and the expenditures, disbursements and cash receipts are for the purposes and objectives set forth in the terms and conditions of the Federal award. I am aware that any false, fictitious, or fraudulent information, or the omission of any material fact, may subject me to criminal, civil or administrative penalties for fraud, false statements, false claims or otherwise. (U.S. Code Title 18, Section 1001 and Title 31, Sections 3729-3730 and 3801-3812).”
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.507 Program-specific audits. | Procurement & Contracting | When agency expends federal funds under only one program and meets the audit threshold, it must conduct a program-specific audit instead of a single audit. Annually, if agency expends $1,000,000 or more in federal awards from a single program. | One-time |  | Conditional | Engage an independent auditor to perform a program-specific audit in accordance with § 200.507 and submit the audit report to the Federal Audit Clearinghouse within required timelines.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.305 Federal payment. ASAP Registration | Financial | Requires registration in the Automated Standard Application for Payments (ASAP) system to receive federal funds. | One-time |  | Applicable | Initiate Automated Standard Application for Payments (ASAP) account setup by submitting organizational and banking information through the ASAP portal.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.305 Federal payment. Proper Payment Drawdown. | Financial | Ensures federal funds are drawn only when needed for immediate disbursement. | One-time |  | Applicable | Verify that drawdown requests align with actual, immediate cash needs before initiating the transaction in ASAP.
RAIN-2018-G05-R2 | EPA Guidance on Participant Support Costs; Definition and Allowability of Participant Support Costs | Financial | Defines participant support costs and clarifies their allowability under EPA financial assistance agreements, including rebates, subsidies, and payments to encourage environmental stewardship. | One-time |  | Applicable | Review the EPA’s Guidance on Participant Support Costs and ensure all proposed participant support costs are categorized and justified according to EPA and Uniform Grants Guidance definitions.
RAIN-2018-G05-R3 | EPA Guidance on Participant Support Costs; Exclusion from Modified Total Direct Costs | Financial | Participant support costs must be excluded from Modified Total Direct Costs when preparing budgets for EPA financial assistance. | One-time |  | Applicable | Exclude participant support costs from Modified Total Direct Costs calculations in all budget documents submitted to EPA.
RAIN-2018-G05-R4 | EPA Guidance on Participant Support Costs; Prior Approval for Budget Changes | Financial | Prior written EPA approval is required if moving budgeted participant support costs to another budget category, per 2 CFR 200.308(f)(5). | One-time |  | Applicable | Submit a formal request to EPA for prior written approval before reallocating participant support costs to another budget category. [rain_2018_g05_r2 ¦ PDF]
RAIN-2018-G05-R5 | EPA Guidance on Participant Support Costs; Documentation of Participant Support Costs | Financial | Requires documentation of participant support costs as outlined in 2 CFR 200.456. | One-time |  | Applicable | Maintain detailed records and supporting documentation for all participant support costs, ensuring compliance with EPA and Uniform Grants Guidance.
RAIN-2018-G05-R6 | EPA Guidance on Participant Support Costs; Benchmarks for Reasonableness | Financial | Provides benchmarks for determining the reasonableness of stipend payments, travel assistance, and incentives for program participants. | One-time |  | Applicable | Compare proposed participant support payments against EPA benchmarks and document justification for amounts exceeding benchmarks.
RAIN-2018-G05-R7 | EPA Guidance on Participant Support Costs; Expanded Definition (Temporary Childcare/Dependent Care) | Financial | The definition of participant support costs now includes temporary childcare and dependent care for program participants. | One-time |  | Not applicable | Include temporary childcare and dependent care as allowable participant support costs in budgets and claims, per updated EPA guidance.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.320 Procurement methods. | Procurement & Contracting | Specifies the allowable methods for procuring goods and services under federal awards, including informal, formal, and noncompetitive procedures | One-time |  | Applicable | Determine the appropriate procurement method (micro-purchase, small purchase, sealed bid, competitive proposal, or noncompetitive) for each transaction, document the rationale, and follow all required procedures and thresholds as outlined in § 200.320
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.319 Competition. | Procurement & Contracting | Requires all procurement transactions under federal awards to be conducted in a manner that provides full and open competition, prohibiting practices that restrict competition | One-time |  | Applicable | Review and document procurement procedures to ensure solicitations are open, fair, and do not include restrictive requirements (such as unnecessary experience, excessive bonding, or brand-name-only specifications); exclude contractors who helped draft specifications from competing.
RAIN-2024-G01 | New Recipient Training Requirement | Procurement & Contracting | All new EPA grant applicants/recipients must complete EPA Grants Management Training and Budget Development Training before receiving grant funds. One-time, prior to receiving EPA grant funds (applies only to organizations that have never received an EPA grant, or last received one before FY2015). [epa.gov] | One-time |  | Conditional | Identify whether your organization qualifies as a “new applicant/recipient” under EPA’s definition, then register for and complete both the EPA Grants Management Training for Applicants and Recipients and the How to Develop a Budget training series.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 1500.12 Quality Assurance. QMP. | Procurement & Contracting | Requires all EPA assistance agreements involving environmentally related data operations to have a written quality assurance system, reviewed and approved by EPA, and implemented by the recipient. | One-time |  | Applicable | Develop a written Quality Management Plan (QMP) and/or Quality Assurance Project Plan (QAPP) that meets EPA standards, submit it to EPA for review and approval, and ensure no environmental data collection begins until EPA approval is received.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 1500.12 Quality Assurance. Performance Measure. | Procurement & Contracting | PA requires recipients to track and report specific performance measures as defined in the assistance agreement. | One-time |  | Applicable | Identify the mandated performance measures in the EPA agreement and establish a tracking system to collect and report data according to EPA’s schedule.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 1500.12 Quality Assurance. Output Deliverable. | Procurement & Contracting | EPA requires recipients to produce and submit specific deliverables as outlined in the assistance agreement. | One-time |  | Applicable | Review the agreement for required deliverables, assign responsibility, and create a submission schedule to ensure timely delivery to EPA.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 1500.12 Quality Assurance. Outcome Linked to Plan. | Procurement & Contracting | EPA mandates that all deliverables and outcomes must be explicitly linked to the organization’s strategic plan or EPA’s strategic goals. | One-time |  | Applicable | Map each deliverable and outcome to the relevant strategic plan objective, document the linkage, and include this mapping in all reports to EPA.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.302 Financial management. | Financial | Requires recipients and subrecipients of federal awards to maintain financial management systems that ensure accurate identification, tracking, and reporting of federal funds, compliance with statutes and award terms, and effective internal controls. | One-time |  | Applicable | Establish and maintain a financial management system that identifies all federal awards, tracks expenditures and balances, ensures accurate and complete financial reporting, and safeguards assets in accordance with § 200.302 requirements.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.304 Bonds. | Financial | Allows federal agencies to require recipients to obtain adequate bonding and insurance when the federal government guarantees or insures repayment of borrowed funds, or when fidelity bond coverage is needed to protect federal interests | One-time |  | Conditional | Review federal award terms to determine if bonding or insurance is required; if so, obtain bonds and insurance from companies authorized by the U.S. Department of Treasury (see 31 CFR part 223) and maintain documentation for compliance.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.306 Cost sharing. | Financial | Establishes requirements for cost sharing or matching contributions, including standards for allowability, documentation, and valuation of third-party in-kind contributions. | One-time |  | Applicable | Identify all cost sharing or matching requirements in the award, ensure contributions are allowable and properly documented, and maintain records that clearly show the source, value, and use of all cost sharing contributions.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.307 Program income. | Financial | Establishes requirements for identifying, using, and reporting program income earned as a result of federally funded projects, including allowable uses and accounting standards. | One-time |  | Not applicable | Identify all sources of program income, ensure income is used and reported according to the federal awarding agency’s specified method (deduction, addition, or cost sharing), and maintain records to support all program income transactions.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.309 Modifications to Period of Performance. | Financial | Requires recipients to only charge allowable costs to federal awards during the period of performance specified in the award, ensuring costs incurred outside this period are not charged unless authorized. | One-time |  | Applicable | Verify that all costs charged to the federal award are incurred within the specified period of performance; review award documents for start and end dates and ensure no costs are charged outside these dates unless prior written approval is obtained.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.515 Audit reporting. | Financial | Requires auditors to issue reports on financial statements, internal controls, and compliance for major programs, including a schedule of findings and questioned costs. Annually, as part of the Single Audit for entities expending $1,000,000 or more in federal awards during the fiscal year. | One-time |  | Conditional | Confirm whether DEQ or its subrecipients meet the Single Audit threshold and initiate engagement with an independent auditor to conduct the audit in accordance with 2 CFR Part 200 Subpart F.
RAIN-2018-G02-R2 | Indirect Cost Policy and Guidance for Recipients of EPA Assistance Agreements | Financial | Provides guidance on allowable indirect cost rates under EPA grants and cooperative agreements, aligning with 2 CFR Part 200 and offering flexibility for recipients | One-time |  | Applicable | Verify that DEQ has a current approved indirect cost rate or elects the de minimis rate (up to 15%) and ensure the EPA-approved budget includes indirect costs before drawing down funds.
Award Agreement; EPA General Terms & Conditions | Subaward Reporting in SAM.gov | Procurement & Contracting | Federal agencies and entities must report each subaward meeting the criteria in award term paragraph 15.1.a to SAM.gov. Within 30 days of the subaward execution or obligation. | One-time |  | Applicable | Log into SAM.gov and submit the required subaward details (including DUNS/UEI, amount, and description) for any new subaward within 30 days of issuance.
Award Agreement; EPA General Terms & Conditions | Build America, Buy America (BABA) | Procurement & Contracting | Federal infrastructure projects must use U.S.-produced iron, steel, manufactured products, and construction materials as mandated by the Build America, Buy America Act (Public Law 117-58). | One-time |  | Applicable | Verify that all vendors and contractors certify U.S. origin for iron, steel, manufactured products, and construction materials before approving purchase orders or contracts. Or submit a waiver request if applicable.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.318 General procurement standards. | Procurement & Contracting | Requires non-Federal entities to maintain documented procurement procedures, ensure contractor oversight, and implement written standards of conduct to prevent conflicts of interest in all federally funded procurements. | One-time |  | Applicable | Review and update DEQ’s procurement policy to ensure it includes documented procedures, contractor oversight provisions, and written conflict-of-interest standards consistent with 2 CFR §§200.317–200.327 before initiating any procurement.
Award Agreement; EPA General Terms & Conditions | 2 CFR § 200.329 Monitoring and reporting program performance. | Procurement & Contracting | Recipients and subrecipients must monitor activities under Federal awards to ensure compliance and submit performance reports that relate financial data to program goals and objectives. | One-time |  | Applicable | Establish a monitoring plan for all CPRG-funded activities and submit semi-annual performance progress reports to EPA that include technical progress, milestones, and budget updates for each measure in the approved work plan.
Award Agreement; EPA General Terms & Conditions | Davis Bacon and Related Acts | Procurement & Contracting | Requires contractors and subcontractors on federally funded construction projects over $2,000 to pay laborers and mechanics prevailing wages and fringe benefits as determined by the U.S. Department of Labor. | One-time |  | Applicable | Include current Davis-Bacon wage determinations and labor standards clauses in all solicitations, contracts, and subawards before work begins, and set up a process to collect and review weekly certified payrolls.
Award Agreement; EPA General Terms & Conditions | EPA Strategic Plan; Document Key Assumptions | Reporting | Recipients must document key assumptions for each measure, including implementation rate, milestones, and lifetime, as part of emissions reporting. | One-time |  | Applicable | Compile and submit documented assumptions for each CPRG measure in the emissions report, ensuring milestones and lifetime estimates are clearly stated.
Award Agreement; EPA General Terms & Conditions | EPA Strategic Plan; Report EV and Infrastructure Metrics | Reporting | Recipients must report the number and type of vehicles replaced by electric vehicles, chargers installed, electric nonroad equipment purchased, and supporting infrastructure. | One-time |  | Conditional | Collect and validate data on electric vehicles replacements, charger installations, and equipment purchases; include these metrics in the one-year and final performance reports.
Award Agreement; EPA General Terms & Conditions | EPA Strategic Plan; Respond to EPA Prompts | Reporting | Recipients must provide narrative responses to EPA-specified prompts regarding outputs, outcomes, planned activities, challenges, successes, and lessons learned for each reporting period. | One-time |  | Applicable | Draft and submit narrative responses addressing all EPA prompts in the required performance report template for each reporting cycle.
Award Agreement | Award Agreement; Two Semi-Annual Reports | Reporting | Submit two semi-annual reports covering specified periods. | One-time |  | Applicable | Prepare October 1 – March 31 semi-annual report by April 30 and the April 1-September 30 semi-annual repot by October 30, including all required technical, financial, and narrative updates.
Award Agreement | Award Agreement; One Annual Report | Reporting | Submit one annual report as required by the agreement. | One-time |  | Applicable | Compile and submit the annual report as part of the second semi-annual report using a template to be provided by EPA.
Award Agreement | Award Agreement; Final Report | Reporting | Submit a final report no later than 120 calendar days after the end of the period of performance. | One-time |  | Applicable | Complete and submit the final report within 120 days of the period of performance end date, ensuring all required sections and certifications are included.
Award Agreement; EPA General Terms & Conditions | Historic Preservation; NHPA Section 106 Review | EHP/Permitting | Assist EPA in complying with Section 106 if activities impact historic properties. | One-time |  | Applicable | Include a Section 106 clause in subawards. Establish a process to collect information from subawards to ensure compliance.
Award Agreement; EPA General Terms & Conditions | Historic Preservation: Archeological and Historic Preservation Act (AHPA) | EHP/Permitting | Preserve important archaeological data in project areas. If project encounters an archaeological site or historic resource that will be destroyed, the agency is responsible for recovering artifacts and recording information before that happens. Archeological and Historic Preservation Act (AHPA) often works in tandem with Section 106, providing the legal basis to spend project funds on salvage archaeology. | One-time |  | Applicable | Include a Section 106 clause in subawards. Subawards should include in construction contracts a clause for “unexpected discovery” of cultural artifacts. If artifacts, burial sites, or other archaeological data are unearthed during construction, stop work in that area and contact a professional archaeologist and the State Historical Preservation Office (SHPO) immediately. Notify EPA and the National Park Service if the data is significant. Develop a Data Recovery Plan (in consultation with SHPO) outlining how you will excavate, document, and curate the finds. Only resume construction after the data recovery is complete and SHPO gives clearance. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Environmental Cross-Cutter Questionnaire & Supporting Documentation Checklist | Native American Graves Protection & Repatriation Act | EHP/Permitting | If a project on federal or tribal land inadvertently discovers Native American human remains or sacred objects, all work must cease and the finds must be respectfully handled in accordance with NAGPRA | One-time |  | Not applicable | Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Environmental Cross-Cutter Questionnaire & Supporting Documentation Checklist | Archaeological Resources Protection Act | EHP/Permitting | Prevent unauthorized digging or artifact collecting on protected lands. ARPA means that if any subaward involves an archaeological study on Federal or Tribal lands a Federal ARPA permit is required. More generally, ensure contractors and staff know not to souvenir-hunt or disturb archaeological sites on public lands. | One-time |  | Applicable | Include language about ARPA in subaward contract. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement ; EPA General Terms & Conditions | Other Federal Requirements : Endangered Species Act (ESA) | EHP/Permitting | Identify and report activities that may involve threatened or endangered species. | One-time |  | Applicable | Include language about Endangered Species Act in subaward contract. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Environmental Cross-Cutter Questionnaire & Supporting Documentation Checklist | Bald & Golden Eagle Protection Act | EHP/Permitting | Confirm each project location does not disturb Bald or Golden Eagles which includes any activity that agitates or bothers eagles to a degree that causes injury, decreased productivity, or nest abandonment. | One-time |  | Applicable | Include language about Bald & Golden Eagle Protection Act in subaward contract. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Environmental Cross-Cutter Questionnaire & Supporting Documentation Checklist | Migratory Bird Treaty Act | EHP/Permitting | Confirm each project will protects migratory birds, along with their nests and eggs, by making it unlawful without a proper permit to pursue, hunt, take, capture, kill or possess migratory birds as well as import, export, transport, sell, or barter birds (including nests, eggs, feathers, etc.) | One-time |  | Applicable | Include language about Migratory Bird Treaty Act in subaward contract. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Environmental Cross-Cutter Questionnaire & Supporting Documentation Checklist | Marine Mammal Protection Act | EHP/Permitting | Confirm each project protects marine mammals in the U.S. by making it illegal to harass, feed, hunt, capture or kill any marine mammal | One-time |  | Not applicable | Include language about Marine Mammal Protection Act in subaward contract (if any projects are near the ocean). Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
EPA Subaward Cross Cutter Requirements ;Environmental Cross-Cutter Questionnaire & Supporting Documentation Checklist | Safe Drinking Water Act, Sole Source Aquifer | EHP/Permitting | Confirm each project will to protect public health by ensuring the quality of drinking water supplied by public water systems. | One-time |  | Applicable | Include language about Safe Drinking Water Act in subaward contract. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement; EPA General Terms & Conditions; EPA Subaward Cross Cutter Requirements | Other Federal Requirements : Farmland Protection Policy Act (FPPA) | EHP/Permitting | Work with EPA/NRCS to identify and mitigate adverse effects on farmland. | One-time |  | Applicable | Provide Subawards with Form AD-1006, evaluate alternatives, document findings. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement; EPA General Terms & Conditions; EPA Subaward Cross Cutter Requirements | Other Federal Requirements : Coastal Zone Management Act (CZMA) | EHP/Permitting | Ensure projects are consistent with state coastal management programs. | One-time |  | Not applicable | Include language about Coastal Zone Management Act in subaward contract (if any projects are in the Coastal Zone). Coordinate with subrecipients if the project is local in Costal Zone Management to notify necessary compliance. Subawards in the Coastal Zone will have to coordinate with state agency for compliance.
Award Agreement; EPA General Terms & Conditions; EPA Subaward Cross Cutter Requirements | Other Federal Requirements : Federal Funding Accountability and Transparency Act (FFATA) Reporting | EHP/Permitting | Recipients must report subawards and executive compensation for actions obligating $30,000 or more in federal funds. This includes reporting the total compensation for the five most highly compensated executives if certain thresholds are met. | One-time |  | Applicable | Coordinate with Finance Team to provide notice about the reporting requirement. Financial officer to use the SAM.gov FSRS module to report any subaward of $30,000 or more within the end of the month after award.
Award Agreement; EPA General Terms & Conditions; EPA Subaward Cross Cutter Requirements | Nondiscrimination Laws and Social Policies: Title VI of the Civil Rights Act | EHP/Permitting | Non-Discrimination Race, Color, National Origin: Recipients of federal funds must not discriminate against any person on the basis of race, color, or national origin in any program or activity. This includes ensuring meaningful access for persons with limited English proficiency. Title VI obligations extend to subrecipients and contractors. | One-time |  | Applicable | Coordinate internally to review Title VI, Section 504 (disability), Age Discrimination, and if applicable Title IX obligations. Update the policies/training to reflect zero tolerance for discrimination. Include language about Title VI in subaward agreement. Provide required non-discrimination notices to participants and subcontractors, and designate a coordinator to handle any complaints.
Award Agreement; EPA General Terms & Conditions; EPA Subaward Cross Cutter Requirements | Nondiscrimination Laws and Social Policies: Section 13 of the Federal Water Pollution Control Act | EHP/Permitting | Commonly known as “Section 13” of the Clean Water Act, it prohibits sex discrimination in any program or activity receiving Federal funds under the Water Pollution Control Act. This applies broadly to program delivery and also to employment practices under the grant. | One-time |  | Applicable | Include language in subaward to include Section 13 of Clean Water Act.
Award Agreement; EPA General Terms & Conditions; EPA Subaward Cross Cutter Requirements | Nondiscrimination Laws and Social Policies: Section 504 of Rehabilitation Act | EHP/Permitting | Recipients and subrecipients must ensure that qualified individuals with disabilities are not excluded from participation, denied benefits, or subjected to discrimination under any program receiving federal assistance. Facilities and communications must be accessible as per Section 504 standards (and ADA). | One-time |  | Conditional | Include language in the subaward about Section 504 compliance. Coordinate internally to evaluate whether any subaward project involves public-facing facilities or services. Ensure no discrimination
EPA Subaward Cross Cutter Requirements | Nondiscrimination Laws and Social Policies: Age Discrimination Act | EHP/Permitting | Federally supported programs cannot exclude, deny benefits to, or subject anyone to discrimination on the basis of age. | One-time |  | Applicable | Include language in the subaward about Age Discrimination Act compliance. Give subrecipients language to include in contracts.
EPA Subaward Cross Cutter Requirements | Nondiscrimination Laws and Social Policies: 40 CRF Part 5 | EHP/Permitting | EPA regulation prohibiting discrimination on the basis of race, color, national origin, sex, or disability. | One-time |  | Applicable | Include language in the subaward about 40 CRF Part 5 to ensure there is not any disclination based on race, color, national origin, sex, or disability. Give subrecipients language to include in contracts.
EPA Subaward Cross Cutter Requirements | Nondiscrimination Laws and Social Policies: 40 CRF Part 7 | EHP/Permitting | 40 CFR Part 7 consolidates requirements for Title VI, Section 504, Age Act, etc., for EPA-funded programs. Recipients must have non-discrimination policies, provide public notices of rights (“EPA Non-Discrimination Notice”), designate a civil rights coordinator, and maintain compliance information and records. | One-time |  | Applicable | Include language in subaward for compliance with 40 CFR 7. Coordinate internally on maintaining records.
EPA Subaward Cross Cutter Requirements | Executive Order 11246 | EHP/Permitting | All construction contracts include the standard Federal EEO clauses and that contractors take affirmative action to ensure fair employment (no discrimination by race, color, religion, sex, sexual orientation, gender identity, or national origin). Contractors with contracts > $10k must have nondiscrimination policies and, if applicable, affirmative action plans. | One-time |  | Applicable | Include language in subaward about Executive Order 11246 compliance. Subawards should include seven nondiscrimination clauses in all construction contracts.
EPA Subaward Cross Cutter Requirements | Executive Order 13798 | EHP/Permitting | Religious organizations are eligible on the same basis as others to participate in federally funded programs, and that agencies must respect religious liberty in grant-funded activities. In short, you cannot discriminate for or against an applicant or beneficiary on the basis of religion. | One-time |  | Applicable | Include language in subaward for Executive Order 13798 compliance. Ensure no discrimination based on religion; review and update policies as needed.
EPA Subaward Cross Cutter Requirements | Disadvantaged Business Enterprises (DBE) Requirements; 40 CRF Part 33 | EHP/Permitting | EPA has suspended certain Disadvantaged Business Enterprises requirements (fair share objectives, reporting, enforcement, Disadvantaged Business Enterprises closeout forms), but other provisions of 40 CFR Part 33 still apply unless specifically waived. | One-time |  | Applicable | Include language in subaward for Disadvantaged Business Enterprises compliance. Coordinate internally to collect documentation from subawards on DBE efforts.
EPA Subaward Cross Cutter Requirements | Consultation with State and Local Officials (EO 12372, 40 CRF Part 29) | EHP/Permitting | Requires intergovernmental review of federal programs and projects. | One-time |  | Applicable | Submit projects for state/local review as required; respond to comments; document compliance.
Award Agreement; EPA Subaward Cross Cutter Requirements | Environmental Authorities: Protection of Wetlands, EO 11990 | EHP/Permitting | Protection of Wetlands: Federal funds should not support construction in wetlands unless there is no practicable alternative. If building in a wetland is necessary, the project must include all possible mitigation to minimize harm | One-time |  | Applicable | Include language in subaward about wetlands protection. Subrecipients will need to identify wetlands, document alternatives, mitigate impacts, retain records. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement; EPA Subaward Cross Cutter Requirements | Environmental Authorities: Floodplain Management, EO 11988 & EO 13690 | EHP/Permitting | Avoid adverse impacts to floodplains by not building in the floodplain; increase resilience to flooding. | One-time |  | Applicable | Identify floodplain, evaluate alternatives, public notice, mitigate impacts, document findings. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement; EPA Subaward Cross Cutter Requirements | Environmental Authorities: Wild and Scenic Rivers Act | EHP/Permitting | Federal assistance cannot directly or adversely affect the values of a designated Wild and Scenic River. If a project is near or on a protected river segment, the agency must consult with the managing authority (e.g., NPS or USFS) to ensure the river’s free-flow, water quality, and “outstanding remarkable values” are not harmed. | One-time |  | Applicable | Include language in subaward about floodplain compliance. Subrecipients will identify proximity, consult managing agency, avoid adverse impacts, document Section 7 review. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement; EPA Subaward Cross Cutter Requirements | Rivers & Harbors Act | EHP/Permitting | Construction of any structure or work in or over navigable waters of the U.S. (e.g., piers, wharves, dredging) requires a Section 10 permit from the Army Corps. This law predates the CWA and specifically protects navigation channels from unapproved obstructions or alterations. | One-time |  | Applicable | Include language in subaward about Rivers & Harbors Act compliance. Subawards to provide all necessary information about if projects impacts Rivers or Harbors (as is appliable per project) Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement; EPA Subaward Cross Cutter Requirements | Environmental Authorities: Magnuson-Stevens Fisheries Conservation and Management Act | EHP/Permitting | If a project may adversely affect Essential Fish Habitat (designated spawning, breeding, feeding, or growth areas for fish), the Federal agency must consult with NOAA Fisheries. | One-time |  | Applicable | Include language in subaward about Essential Fish Habitat compliance. Subawards will identify Essential Fish Habitat, consult National Marine Fisheries Service (NMFS), implement recommendations, document review. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
Award Agreement; EPA Subaward Cross Cutter Requirements | Clean Air Conformity Act | EHP/Permitting | Federal agencies must ensure their actions conform to the State Implementation Plan for air quality in nonattainment or maintenance areas. Federally funded project cannot cause new air quality violations or worsen existing ones. | One-time |  | Applicable | Include language in subaward about Clean Air Conformity Act for compliance. Provide subrecipients with Environmental Cross-Cutting Checklist to complete for each project.
EPA Subaward Cross Cutter Requirements | National Defense: Never Contract with the Enemy (P.L. 113-91) | EHP/Permitting | Requires subrecipients must comply with Section 889 of the National Defense Authorization Act (NDAA) and 2 CFR §200.216 | One-time |  | Not applicable | Does not apply
EPA Subaward Cross Cutter Requirements | National Defense: Prohibition using Federal funds for certain telecommunications and video surveillance services or equipment (Section 889 of P.L. 115-232). | EHP/Permitting | Ensure funds are not used to procure or contract for telecommunications or video surveillance equipment or services from Huawei, ZTE, Hytera, Hikvision, Dahua, or their affiliates, as prohibited under Section 889 of Public Law 115-232 | One-time |  | Conditional | Add a clause to the subaward agreement to ensure compliance for telecommunication.
EPA General Terms & Conditions | Performance Reporting - Subaward Performance Reporting | Reporting/Forms | Recipient must include in its grant performance reports a summary of how it monitored subrecipients to ensure compliance and performance, as required by 2 CRF 200.332(d). | One-time |  | Applicable | Provide form to subrecipients. Sub-recipients must submit report monitoring activities for subawards in accordance with 2 CFR 200.332(d).
EPA General Terms & Conditions | Performance Reporting - Lobbying Activities | Performance Reporting & Compliance | Lobby form to certify lobbying requirements upon contract execution. | One-time |  | Applicable | Provide form to subrecipients. Subrecipients must submit a lobbying certification form (SF-LLL) upon contract execution.
EPA General Terms & Conditions | Performance Reporting - Lobbying Litigation | Performance Reporting & Compliance | After the entire project period ends (including all contracts and subawards), the prime recipient must certify that no federal funds were used for lobbying or prohibited litigation activities during the life of the award. | One-time |  | Applicable | Provide form to subrecipients. Subrecipients must submit the lobbying and litigation certificate within 30 days after the project period ends. Lobbying & Litigation Certification (EPA Form 5700-53
| Environmental and CR Compliance - EJ | EHP/Permitting | Report must include detailed data through an EPA-provided electronic interface, covering co-pollutant emissions reductions by pollutant, sector, and county. | One-time |  | Applicable | Provide a report on co-pollutant analysis and community engagement in environmental justice compliance.
Award Agreement | Environmental and CR Compliance - Civil Rights | EHP/Permitting | Must comply with Title VI and EPA's nondiscrimination regs. | One-time |  | Applicable | Include language in subaward agreement for compliance. Review internal policies to ensure compliance. Comply with Title VI and EPA nondiscrimination regulations.
Award Agreement | Records Retention - CIO 2155.5 | Performance Reporting & Compliance | Record keeping is in compliance with CIO 2155.5 and NARA standards. All financial documentation (invoices, drawdown records), correspondence, reports, subrecipient files, and procurement records must be retained and accessible for 3 years from the submission of the final expenditure report. | One-time |  | Applicable | Include language in subaward agree about maintaining records for compliance. Coordinate internally about record keeping practices. Maintain records in compliance with CIO 2155.5 and NARA standards.
Award Agreement | Programmatic Condition p.12 | Data Collection | For projects involving environmental data collection (e.g., emissions measurements, air monitoring, modeling), Quality Assurance Project Plans (QAPPs) must be developed and submitted within 60 days of project selection. | One-time |  | Applicable | Develop a Quality Assurance Project Plan (QAPP) template for subawards based on EPA guidance: https://www.epa.gov/system/files/documents/2025-10/qapp-guidance_dtd_10012025_1.pdf Provide subawards with template to fill out and submit QAPPs within 60 days of grant selection for data collection activities. Within 60 days of grant selection
Award Agreement | Programmatic Conditions p.12 | Quality Management | The organization must have a broader Quality Management Plan (QMP) to cover how it manages quality for the grant project, to be submitted to EPA within 60 days. The QMP is an umbrella document describing the quality system (training, document control, review processes) for all grant activities. | One-time |  | Applicable | Develop a Quality Management Plan (QMP) template for subawards based on EPA guidance: https://www.epa.gov/sites/default/files/2016-06/documents/r2-final.pdf Prepare and submit a QMP to EPA within 60 days of grant award. Within 60 days of grant award
Award Agreement | Programmatic Conditions p.2 | Methodologies | All greenhouse gas inventories, calculations, and projections must use EPA-approved or standard methodologies. This ensures consistency and credibility of emission reduction estimates (e.g., using EPA’s Greenhouse Gas Inventory guidance or approved calculators). | One-time |  | Applicable | Coordinate with the Technical staff to create a list of EPA GHG Inventory Methods. Use only EPA-approved methodologies for greenhouse gas data and projections; review EPA guidance before starting analysis.
Award Agreement | Programmatic Conditions p.9 | Data Quality & Transparency | All data produced by the project must be made publicly available in a machine-readable format. The condition discourages using handwritten logs or non-digital formats; instead, sharing datasets via online platforms. The goal is to promote transparency and allow others to review or use the data. | One-time |  | Applicable | Coordinate with IT to develop a plan to collect and publish all data publicly. Ensure all project data is made public and machine-readable; avoid handwritten records and use digital formats for greater transparency and reputability.
Award Agreement | Programmatic Conditions p.9 | Security | The recipient must adhere to all applicable state IT security standards for systems used in the project (and ensure subrecipients do as well). This likely references Virginia state policies (e.g., SEC 525) as well as any federal cyber requirements. It covers protection of sensitive data, proper use of state networks, etc. | One-time |  | Applicable | Coordinate with IT to review state regulations and align internal policies; Review and follow all state cybersecurity requirements for data systems and subawards; ensure subrecipients are also compliant.
Award Agreement | Programmatic Conditions p.9 | Performance Reporting & Compliance | The recipient must incorporate consideration of future climate conditions in project design. | One-time |  | Conditional | Establish a process to document incorporate of current and future risk in the all aspects of the proposed project(s). Assess and incorporate future climate risks into all phases of project planning, design, and implementation.
Award Agreement | Programmatic Conditions p.10 | Equipment/Materials | Any equipment purchased to replace existing equipment must have the same function and capacity as the original. | One-time |  | Conditional | Include langue in the subaward about proper procurement procedures and ensure that equipment purchased is an equivalent-function replacement. Coordinate with subrecipients to ensure the new equipment performs a similar function to the original; document the comparison.
Award Agreement | Programmatic Conditions p.10 | Equipment/Materials | Replacement equipment must reduce emissions per the EPA-approved work plan. Replacement equipment must meet at least the same or better emission standards as committed in the application (often meaning lower emissions than the old equipment). | One-time |  | Conditional | Include language in the subaward about following the emission reductions targets for new equipment. Coordinate with subrecipients to ensure all replacement equipment reduces emissions as outlined in the EPA-approved work plan; verify and document compliance.
Award Agreement | Programmatic Conditions p.10 | Equipment/Materials | Replacement equipment must match intended use, operation, and location as described in the work plan. The recipient must operate and maintain the funded equipment in accordance with manufacturer recommendations and EPA guidelines. This is to ensure the equipment actually delivers its environmental benefits over its lifespan. | One-time |  | Conditional | Include language in the subaward about replacing equipment that matches intended use, operation, and location. Coordinate with subrecipients to confirm that replacement equipment matches the intended use, operation, and location as described in the EPA-approved work plan; document alignment.
Award Agreement | Programmatic Conditions p.10 | Equipment/Materials | The recipient/ sub-recipient must operate and maintain the funded equipment in accordance with manufacturer recommendations and EPA guidelines. | One-time |  | Conditional | Include language in the subaward about collecting information from subawards on how systems will be maintained for reporting. Coordinate with subrecipients to they are operating and maintaining all systems, equipment, and devices according to manufacturer and EPA guidelines; train staff and subrecipients as needed. Coordinate internally on how to collect data.
Award Agreement | 2 CFR 200.1 & 200.313 | Procurement & Contracting | The Uniform Guidance property rules apply: the state must keep inventory records of all equipment bought with grant funds, ensure it's used for the project (or other federal projects if allowed later), and prevent loss or theft. When equipment is no longer needed, disposition must follow 2 CFR 200.313 (e.g., if value >$5k, may need to reimburse federal share or get approval to transfer). | One-time |  | Conditional | Develop a process to inform/verify subawards procurement policies align with state and federal regulations. Follow 2 CFR 200.1 and 200.313 requirements when acquiring equipment; maintain documentation of procurement process and compliance.
Award Agreement | Programmatic Conditions p.15 | Equipment/Materials | Recipient/ Sub-recipient may not encumber the equipment as collateral or otherwise without EPA (or pass-through) approval. The subrecipient cannot take out a loan against the grant-funded equipment or lease it out in a way that puts a lien on it. It must remain free and clear for project use. | One-time |  | Conditional | Include language in the subaward agreement about not being allowed to encumber the equipment.
Award Agreement | Programmatic Conditions p.15 | Equipment/Materials | All equipment must be used and disposed in compliance with all applicable federal, state, and local laws. | One-time |  | Conditional | Include language in the subaward agreement about proper disposal of equipment/materials. Provide subrecipients with language to include in contracts.
Award Agreement | Programmatic Conditions p.15 | Equipment/Materials | For state-owned equipment, title vests in the state, but at the end of the project, if equipment is no longer needed for the program, it should be disposed according to state law/procedure. | One-time |  | Conditional | Coordinate with state agencies on compliance if necessary.
Award Agreement | Davis-Bacon and Related Acts (DBRA) | Procurement & Contracting | Requires contractors and subcontractors on federally funded construction projects over $2,000 to pay laborers and mechanics prevailing wages and fringe benefits as determined by the U.S. Department of Labor. | One-time |  | Applicable | Include DBRA language in the subaward agreement for prevailing wage compliance on construction projects. Provide subrecipients with language to include in construction contracts about comply with DBRA.
Award Agreement | Programmatic Condition p.14 | Financial Management | Program income will be added to committed funds for the purpose defined under the assistance agreement. A description of how this fund is being used is required in each performance report. | One-time |  | Not applicable | If a project will be generating income add a clause to subaward agreement to comply with added to committed funds.
Award Agreement | Programmatic Condition p.16 | Real Property Management | If the title is retained, Recipient must compensate the federal agency based on original purchase, improvements, and fair market value. | One-time |  | Not applicable | Identify a process to reimburse EPA for retained real property value. Add program income to committed project funds; describe how program income is used in each performance report and maintain supporting documentation.
Award Agreement | Programmatic Condition p.16 | Real Property Management | If the title is sold , Recipient must compensate the federal agency based on its share of sale proceeds, less reasonable expenses. | One-time |  | Not applicable | Calculate EPA's funding percentage of the original costs plus improvements. If retaining title to real property, calculate and compensate the federal agency based on purchase cost, improvements, and current fair market value; document transaction.
Award Agreement | Programmatic Condition p.16 | Real Property Management | If the title is transferred, it may be transferred to another federal agency or an approved third-party. | One-time |  | Not applicable | Transfer real property only with EPA approval. If the project calls for conveying title of land or structures to another entity, work with EPA in advance to identify an approved Federal agency or third-party recipient
Award Agreement | eCFR :: 2 CFR 200.316 -- Property trust relationship. | Real Property Management | Recipients and subrecipients maintain appropriate records and controls over intangible property (such as copyrights, patents, and data) developed or acquired under a federal award. | One-time |  | Not applicable | Record grant conditions on property title. Comply with 2 CFR 200.316 for real property recordation; review regulation and update property records accordingly.
Award Agreement | Programmatic Condition p.16 | Real Property Management | Recipient must record a lien or similar notice in the property records local to where the real property is located. | One-time |  | Not applicable | Maintain real property compliance records.. Record a lien or similar notice in local property records for federally funded real property; ensure documentation is complete and accessible.
Award Agreement | Programmatic Condition p.17 | Public Communications | The recipient is restricted from using EPA’s logo on materials without permission, and must not imply EPA endorsement of products or services. Any public reference to EPA funding should clarify it’s via financial support, not EPA running the project. | One-time |  | Applicable | Include language about EPA branding requirements in the subaward agreements. Provide subrecipients with EPA branding materials.
Award Agreement | Programmatic Condition p.17 | Public Communications | All publications, presentations, and public communications about the project must acknowledge EPA funding. | One-time |  | Applicable | Include language about EPA funding requirements in the subaward agreements and in any public-facing materials related to CPRG-funded programs.
Award Agreement | Programmatic Condition p.17 | Public Communications | If the grant involves infrastructure projects, the recipient may be required to post a sign at construction sites featuring the “Investing in America – EPA” logo or emblem. | One-time |  | Not applicable (rescinded in mod 1) | Include language about EPA signage requirements in the subaward agreements.
Award Agreement | Programmatic Condition p.17 | Public Communications | Recipients are encouraged to notify (with at least 10-day notice) EPA Project Officer of any public or media events that highlight major accomplishments related to the construction project. | One-time |  | Applicable | Include language about EPA event notice requirements in the subaward agreements. Notify EPA Project Officer at least 10-days in advance of any public or media events highlighting project accomplishments. Coordinate internally about notifying EPA on any PR/media events.
Award Agreement | Programmatic Condition p.18 | Participant Support | Recipient must ensure EPA funds used for student aid are only for U.S Citizens, U.S nationals, or lawful permanent residents. | One-time |  | Conditional | Include language about citizenship/residency requirements for followships/internships in the subaward agreement.
Award Agreement | Programmatic Condition p.19 | Participant Support | Recipient and program participants are responsible for taxes. | One-time |  | Conditional | Develop tax liability language to include in subaward agreements.
Award Agreement | 3 CFR Part 180 | Participant Support | Recipient must not make payments to individuals who are excluded from federal programs under 2 CFR Part 180. | One-time |  | Applicable | Confirm the subrecipients are eligible to receive federal funding and are not debarred using SAM.gov. Add language to subaward agreement about eligible participation. Provide subrecipients with directions to check status prior to payments.
Award Agreement | Programmatic Condition p.19 | Participant Support | Recipient must check participant eligibility using the System for Award Management (SAM.gov) or obtain eligibility certifications from participants. | One-time |  | Applicable | Add language to subaward agreement to about eligible participation. Provide subrecipients with directions to search SAM.gov or collect signed eligibility certifications before disbursing funds. Confirm eligibility of all participants. Verify participant eligibility using SAM.gov or obtain eligibility certifications.
Award Agreement | EPA Policy Directive FEM-2012-02 | Data Quality | All recipients must comply with Agency Policy Directive Number FEM-2012-02, Policy to Assure the Competency of Organizations Generating Environmental Measurement Data under Agency-Funded Assistance Agreements. | One-time |  | Applicable | Review the directive and ensure staff qualifications and Quality Assurance procedures are documented.
Award Agreement | Programmatic Condition p.19 | Data Quality | Recipients must maintain competency through the duration of the project period and document this condition in annual reports. | One-time |  | Applicable | Develop a process to collect information on competency status and any updates in each annual performance report. Maintain and document competency throughout the project period.
Award Agreement | Programmatic Condition p.18 | Data Standards | Geospatial data must be consistent with Federal Geographic Data Committee standards. | One-time |  | Applicable | Coordinate with GIS team to review Federal Geographic Data Committee guidelines and establish a process to validate data from subawards. Geospatial data must comply with Federal Geographic Data Committee standards.
Award Agreement | Programmatic Condition p.18 | Health & Safety | Recipient must have a Health and Safety plan to protect all relevant parties. | One-time |  | Applicable | Add language to subaward agreement about health and safety plan requirements. Provide subrecipients with EPA guide on plan.
Award Agreement | OSHA 29 CFR 1910.120 | Health & Safety | Recipient must ensure the Health and Safety plan complies with OSHA 29 CFR 1920.120 | One-time |  | Applicable | Coordinate with subrecipients about Plan prior to issuing funds. Coordinate internally on verification of plans.
Award Agreement | Programmatic Condition p.18 | Site Access & Security | Recipient must follow instructions from the EPA project officer regarding EPASS compliance. | One-time |  | Conditional | If necessary, coordinate with EPA Project Officer to initiate background checks and access procedures. Comply with EPA’s EPASS security protocols.
Award Agreement | Programmatic Condition p.19 | Financial Compliance | Recipient must not directly or indirectly transfer EPA funds to any Foreign Entity of Concern (FEOC). | One-time |  | Applicable | Include language in subaward agreement to ensure 0 funds are transferred to Foreign Entity of Concern (FEOC.) Do not transfer EPA funds to any FEOC, directly or indirectly
Workplan | Greenhouse Gas (GHG) Emissions Data | Reporting/Forms | Report annual reduction in CO₂e emissions from coal mine methane (CMM) outgassing (target: 1 million metric tons CO₂e/year); Report Baseline emissions from participating coal mines (active and abandoned); Report GHG reductions achieved per project, including comparisons to baseline; | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Impact of GHG Reduction Measures: Methane Capture and Utilization Metrics | Reporting/Forms | Track methane capture rates Monitor and report co-pollutant reductions Methane emission reductions (lbs.) 2025-2030 VOC emission reductions (lbs.) 2025-2030 HAP emission reductions (lbs.) 2025-2030 Methane emission reductions (lbs.) 2025-2050 VOC emission reductions (lbs.) 2025-2050 HAP emission reductions (lbs.) 2025-2050 | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Environmental Results- Outputs, outcomes, and performance measures: Short Term Expected Outputs and Outcomes | Reporting/Forms | Document Advisory Committee membership, roles, and maintain records of all meetings held. Draft and finalize policy options and recommendations for methane capture and utilization. Track and report community engagement metrics including attendance numbers and qualitative feedback. Maintain detailed contractor procurement documentation including competitive process records and selection criteria. Develop and finalize site selection criteria and secure agreements (MOUs or property agreements) for project locations. | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Environmental Results- Outputs, outcomes, and performance measures: Medium Term Expected Outputs and Outcomes | Reporting/Forms | Report methane flow rates and capture efficiency at test sites. Report emissions reduction estimates refined with DEQ and third-party contractor. Report LCA results for fuel cell and other methane utilization technologies. Report draft and final versions of the initial assessment report. | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Environmental Results- Outputs, outcomes, and performance measures: Long Term Expected Outputs and Outcomes | Reporting/Forms | Report number and performance metrics of installed wells. Report methane removal volumes and conversion efficiency. Report GHG reductions including: Methane, NOx (>99% reduction over venting), CO (99% reduction), VOCs (98% reduction), CO₂ (80% reduction over flaring). Report fuel cell system specifications and operational performance data. | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Job Quality: Job Creation Metrics | Reporting/Forms | Report number of jobs created or retained. Report types of jobs (e.g., apprenticeships, internships, middle-skill careers). Report geographic distribution, especially in disadvantaged communities (e.g., coalfield counties). | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Job Quality: Training Program Metrics | Reporting/Forms | Report on enrollment and completion rates in pre-apprenticeship and registered apprenticeship programs. Report on credentials awarded through partnerships with community colleges. Report participation by underrepresented groups and displaced workers | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Community Benefit: Justice40 Initiative | Reporting/Forms | Identification of disadvantaged communities using CEJST and EPA EJScreen tools (not required just captured) Quantification of benefits (e.g., reduced emissions, improved health outcomes, job creation). | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Community Benefit: Workforce Development and Apprenticeship | Reporting/Forms | Report number of posted opportunities. Report candidate pool size. Report number of local candidates and hires. Report average salaries. Report certifications and credentials awarded | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data
Workplan | Community Benefit: Engagement Strategy | Reporting/Forms | Report document stakeholder concerns and integrate them into project planning. Report on outreach efforts (e.g., flyers, social media, mailers) and meeting attendance | One-time |  | Applicable | Coordinate internally to collect all necessary reporting data metrics from subrecipients. Submit data